## 1 GIA
Gender impact assessments
Table 1 - Gender impact assessments progress
Required | Required | Required | Required | Required | Required | Recommended | Recommended
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Audio-Visual Recording Policy | Policy | The policy sets out the framework for livestreaming and audio visual recording of public council meetings to provide more flexibility in how people participate in council meetings and council decision making. | New | No action taken | No differences in impacts, the practice provides improved access for all people. There is opportunity to increase access to council decision making for a variety of persons who cannot currently attend meetings due to employment, education and disability. | No
Central Registration Enrolment Scheme (CRES) | Policy | The CRES is a new online system for kindergarten enrolments that aims to simplify access to kindergarten services for families and carers. It also aims to increase kindergarten participation and, through this, provide better outcomes for children. | New | No action taken | There is no evidence/data collected in this assessment that changes any aspects or details of the policy. | No
Municipal Public Health and Wellbeing Plan | Program | The priorities of the Plan are based on analysis of the data in relation to the health and wellbeing of the Northern Grampians community, examination of the research of effective service planning and delivery targeted at improving health and wellbeing outcomes and importantly, discussions with key stakeholders within council, key service providers and the community more broadly about what is important to them. The Action Plan will developed in partnership with our stakeholders - Council officers, community, education and community service providers and the community - building on existing work and innovation across the municipality. The process will be dynamic and adaptive as engagement and involvement of key stakeholders increases. | New | No action taken | A detailed analysis has been undertaken by Grampians Women's Health. This is an attachment to the MPHWP Supporting document. Importantly, family violence impacts women significantly. This is well-researched and will form the basis of the actions for the primary goal of preventing family violence which a critical part of the Plan | The Plan is focussed on addressing health and wellbeing concerns of all people in the community, with particular reference to women, people living with disability, Aboriginal and Torres Strait Islander people and other people in our community who experience health disadvantage.
Child Safety and Wellbeing Policy | Policy | This policy outlines Northern Grampians Shire Council’s commitment to the health, safety and wellbeing of all children and to protecting them from child abuse in line with the introduction of new Child Safe Standards from 1 July 2022. | New | No action taken | The Child Safe Standards require respect for diverse needs and upholding equity in the implementation of all policies and procedures within council. Staff and volunteer training as part of the Child Safety and Wellbeing Policy roll out will broaden understanding of gender in the framework of child safety. | No
General Local Law | Service | Ensuring the safety and amenity for all residents and visitors to our shire, across a range of areas. | New | No action taken | We have sourced public endorsement and have communicated our Councils commitment to act to advance gender equality, diversity and active citizenship. Councils Gender equity strategy will report to the community annually on any achievement | There is no evidence that the General Local law impacts any gender more than another
Complaints Policy | Policy | Complaint Handling policy, framework for a consistent council-wide approach to dealing with complaints and documents the complaint handling processes to enable an accessible, responsive, and transparent service to customers | For Review | Yes | The Complaints Policy is a policy that already exists for council and members of the public. The policy is being updated to include the new Child Safety Standards. Council has considered relevant gender equality principles in this policy. Officers will actively assist people with a range of needs to complain and navigate the complaints process. We will treat everyone fairly and respectfully.
Family Violence Policy | Policy | The policy has been written in consultation with employees from the People and Culture team at NGSC. Whilst the policy is primarily aimed at NGSC employyes, to enshrine their right to employer support, the role of NGSC in the prevention of Family Violence will be amplified, with this policy providing a leading example to the community . | New | No action taken | All managers will act to promote employee safety and wellbeing whilst exercising the highest degree of confidentiality when providing support. Assistance for all employees shall be enshrined within our Enterprise Agreement, including the provision of special leave and flexible work practices. All employees will be afforded access to the Employee Engagement Program and awareness activities such as training, events and communications
Great Western Clubrooms Upgrade Project | Service | We are designing the Clubrooms to suit the needs of the whole community considering the existing facilities are focused on a male environment. Whilst acknowledging this, the existing facilities do not meet preferred facility standards for any genders participating in the sports of Netball, AFL, cricket or community sport in general therefore an upgrade to current standards is required. | New | No action taken | The facilities are accessible for all, with paths being wide, flat and maintained well enough to accommodate for wheelchairs, prams and other assistance/mobility aids. People in wheelchairs, assisting people with wheelchairs/mobility aids and people with prams can access the facilities and all areas of need including seating areas and toilets, with ease from the carparks, accessible drinking fountain for people in a wheelchair to access. There is no obvious exclusion of groups, overall the spaces will be inviting for all diverse groups, including facilities such as unisex toilets.The existing processes has resulted in no changes to the project methodology to achieve the best outcome possible. | Yes | When designing new clubrooms we want the spaces to feel welcoming and accessible to all. This includes design in changerooms, amenities and social environments. Design will be mindful of cultures and acceptability through this process.
Central Park Female Friendly Change Rooms Project | Service | We have designed for construction the Change rooms and Lift to suit the needs of the whole community. The existing changerooms are focused on a male environment and the only access to the first floor is a staircase. Whilst acknowledging this, the existing facilities do not meet preferred facility standards for any genders participating in the sports of Netball, AFL, cricket or community sport in general therefore an upgrade to current standards is required. | New | Yes | When designing new clubrooms we want the spaces to feel welcoming and accessible to all. This includes design in changerooms, unisex amenities and social environments. Design will be mindful of cultures, genders and acceptability through this process. Baby change facilities/parents rooms that are separate to the women’s bathrooms will be available. Hot water available or places to heat up bottles will be accessed in the kitchen or canteen. | Yes | Design will be mindful of cultures, genders, access, ability and acceptability through this process. Accessible toilet and shower is a part of the new design. There is an accessible toilet to be installed on the first floor. The lift access to the first floor is a stretch lift which is larger than a normal domestic lift or one that is used in a regional setting due to minimal use expected. The expectations are that this particular lift will be used by parents with prams, older people with limited mobility, people with a disability or injured sportspeople therefore the equipment will be used to a high degree. The size is important for safe access with carers, emergency staff and managing equipment transport.
NGSC Sport and Active Recreation Strategy 2023-2033 | Policy | This Strategy will guide the next ten years of infrastructure planning and programming or activation. The intention of the document is to understand the current and future Sport and Active Recreation needs of the Shire and ensure a sound strategic base to advocate for funding and resources from internal and external sources. | New | Yes | The project is to identify impacts for different groups through extensive engagement. For this to be effective, Council and the consultant will seek input from key organisations and community members to ensure representation is identified and sought. There will be a check point during the whole process to review the progress, quality and detail of information and consider any needs for increased or targeted consultation. The strategy is about gathering information to inform the next 10 years of Councils Actions/work plan that will deliver equitable and accessible infrastructure, activation of spaces and participation in sport and recreation from all community members. | Yes
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Title | Subject | Description | Status | Confirm if actions taken | Describe actions taken | Confirm intersectionality considered | Explain intersectional lens applied
Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review | Yes | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. | Yes | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.

## 2.1 Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required | Recommended | Recommended | Recommended | Recommended
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | Indicators key
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator. | [6 empty] | 1. 2. 3. 4. 5. 6. 7. | Gender composition of all levels of the workforce. Gender composition of governing bodies. Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender. Sexual harassment in the workplace Recruitment and promotion practices in the workplace. Availability and utilisation of terms, conditions and pratices relating to: - family violence leave - flexible working arrangements - working arrangements supporting employees with family or caring responsibilities Gendered segregation within the workplace
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | 1 | 2 | 3 | 4 | 5 | 6 | 7
Implement compulsory Gender Equality Training through the NGSC Learning and Development Hub in line with the Annual Appraisal Process. | Ongoing | • Gender Equality Training will now be included as part of the new Preventing Family Violence Training • Online Training module has been identified (September 2023) for completion by all employees by August 2024, after which the training will be added to Induction for new employees. • Training session for Councillors will be run in December 2023 • Face to Face training completed by 18 employees in May 2023, further sessions planned in November/December 2023. | 100% of employees undertake set training | Modules identified and actively completed by 31/8/2024 | People & Culture |  |  |  | x
Implement advancement strategies such as mentoring and scholarship opportunities that ensure gender equality. | Complete | •In 2022, 21 NGSC employees including co-ordinators commenced a 12-month Leadership training course which includes managing gender equality. •As part of the Prevention of Family Violence program, an Advisory Group was established- a function of this group will include mentoring other staff to embed PFV and GE initiatives. |  | Feb 2023 | People & Culture and Prevention of Family Violence Project Officer |  |  |  |  | x
Develop and implement Senior Leadership Team (SLT) KPIs that ensure leaders are measured on their implementation of gender equality measures in the management of their teams. | In progress | With the appointment of the PFV project officer this action has been extended until 2023/24 financial year to align with delivery of PFV activity |  | 2024-02-01 | People & Culture manager & Prevention of Family Violence Project Officer |  |  |  |  | x | x
Ensure, where appropriate, that leadership training includes gender equality discussions and activities. | In progress | • Gender Equality Training will now be included as part of the new Preventing Family Violence training being developed and due to be delivered in 2023 to employees and Councillors • Staff survey to be implemented in Feb 2023 will inform training content. • Gender Equality & PFV activities will be regularly implemented through cuppa session and Employee Matters. | Gender Equality Training is ongoing- face to face training delivered in 2023, online training to be completed by September 2024 by all employees. • Staff survey to be implemented in Feb 2023 • Gender Equality & PFV activities delivered monthly in Employee Matters and quarterly at cuppa sessions | by 31/12/2023 | People & Culture |  |  |  | x
Review and implement an improved NGSC EO, Bullying and Harassment Policy and Procedure. | Void/cancelled | The manager of P & C who had instigated this change left the organization in May 2023 and as yet it has not been actioned. |  |  | People & Culture
Review and improve the NGSC Exit Procedure to ensure data is captured on gender equality specific issues. | Complete | Completed 30/11/22 Questions added: Do you feel NGSC has strategies/programs/initiatives in place to support and retain women and gender-diverse people in leadership roles. Did you ever feel your gender was a barrier to success, such as being less likely to be promoted, given leadership opportunities, being offered the chance to participate in training? Do you feel confident that if you needed to access support for family violence, that your request would be responded to in a sensitive and timely manner? For part time employees: Did you feel that working part-time/taking up flexible work arrangements excluded you from leadership opportunities? | Implement the improved Exit Procedure and set up a system to record the data from these interviews | by 30/6/2023 | People & Culture |  |  |  | x | x | x
Set up more formal systems to gather employee/gender specific data at Recruitment and Induction. | Complete | Scout (recruitment platform) is now recording gender identity at recruitment. |  | System established with recording processes in place by 30/6/2023 | People & Culture |  |  |  |  | x |  | x
Actively encourage increased participation in People Matters and gender specific surveys | Complete | Staff survey specific to understanding of PFV/GE in Feb 2023 resulted in 60 responses. People Matter Survey result was 88 of 230, response rate of 38% | • Promote the People Matter Survey for 2023, aim for 50 responses | 2023-07-01 | People & Culture | x | x | x | x | x | x | x
Take active steps to attain more complete data on the reasons for female part time and casual participation in the NGSC workforce | In progress | Questionnaire will be sent to all femaile part-time employees in October 2023. NGSC partiipated in research by Dr Cathy Tischler for the Rurality and Workforce Participation: Exploring Prevalence of Part-time andInsecure Work in Grampians Public Sector Roles
Select one
IMPORTANT: When inserting new row(s) to this table, please ensure they are inserted above these two black rows.
Example(s)
Strategies and measures | Status | Status description | Evaluation of success | Timeline | Responsible | Relevant indicator(s)
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X

## 2.2 Resourcing your GEAP
Resourcing your GEAP
Table 2.2 - Allocation of resources to implement the strategies and measures in your GEAP
Recommended
You might consider some or all of the following, in addition to any other aspects you consider relevant: • Who implements the strategies and measures in your GEAP? What role do they perform at what level in your defined entity? • How many staff members/FTE are allocated to implementing the strategies and measures? • Was enough resourcing allocated to successfully implement your strategies and measures? If not, how will this be addressed?
Your Comments
Implementing the strategies and measures in the GEAP primarily fall under the remit of 2 Project Officers within Council, from the People and Culture team and the Community Care team. These 2 staff members allocate approxmately 4 hours per fortnight to implement actions from the GEAP, which is an adequate resource for a small council. Completing the Gender Equality Reporting requirements, however, has taken significantly more time and involved a disproportionate number of staff. It is estimated that completing the report has taken approximately 80 hours of staff time.

## 3 Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required | Recommended | [6 empty] | Recommended | Factors key:
|  |  | Factors | [7 empty] | a. b. c. d. e. f. g. | The size of the defined entity, including the defined entity's number of employees. The nature and circumstances of the defined entity, including any barriers to making progress. Requirements that apply to the defined entity under any other Act, including an Act of the Commonwealth. The defined entity's resources. The defined entity's operational priorities and competing operational obligations. The practicability and cost to the defined entity of making progress. Genuine attempts made by the defined entity to make progress.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
Indicator | Confirm if progress made | Progress description | a | b | c | d | e | f | g | Factors discussion
Gender composition of all levels of the workforce | Yes | In 2021 the composition of the workforce comprised 55% female and 45%male. In 2023, the rate of female representation in the workforce has risen to 57%. Northern Grampians Shire Council has implemented a new Recruitment Policy and Procedure that seeks to ensure gender neutral recruitment practices. The Procedure refers to the Equal Employment Opportunity legislation and allows the hiring Manager to actively participate during the recruitment and onboarding of new employees. Northern Grampains Shire Council has als recently established more formal systems to gather employee/gender specific data at Recruitment and Induction.
Gender composition of governing bodies | Yes | In 2021 the Governing body consisted of 6 males/1 female. In 2023 the representation of females has increased to 29% (up from 14% in 2021).
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | Yes | The gender pay gap in 2021 was 1.9%. In 2023 the gender pay gap has decreased to -0.9%. Northern Grampians Shire Council operates under an Enterprise Bargaining Agreement with a “Pay Banding System” that ensures fair and equal pay for all employees. It ensures that all employees working in the same position are paid at the same rate.
Sexual harassment in the workplace | No | In 2021, 5% of women reported experiencing sexual harrassment behaviours at work. In 2023, 4% of women and 3% of men reported experiencing sexual harrassment behaviours at work, however there were no formal complaints submitted. A key action for the GEAP was for an improved platform for reporting sexual harrassment & violence, including a new conflict resolution procedure, and awareness raising activities (such as posts in Employee matters). In addition, exit procedure questions are now more specific to gather data on sexual harrassment.
Recruitment and promotion practices in the workplace | Yes | The recruitment of women has risen from 51% in 2021, to 59% in 2023. Internal secondments rose by 5%, from 38% in 2021 to 43% in 2023.An action from the GEAP is to "implement advancement strategies such as mentoring and scholarship opportunities that ensure gender equality". The Northern Grampians Shire Council also has a formal Higher Duties Procedure intended to broaden the experience base of staff and facilitate greater flexibility within the organisation. Managers/Supervisors assess the duties to be performed and the period of higher duty appointment to ensure that the conditions of appointment and application is fair and equitable.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | In 2021, 64% of women and 36% of men took parental leave. In 2023, 40% of the workforce are on a formal flexible working arrangement, of which 58% of these are women. In 2023, data shows that 36% of women took parental leave for 49.5 weeks, in comparison to 76 weeks in 2021. Actions taken as part of the GEAP include a Flexible Work Practice and Procedure, allowing several flexible work practice options for employees to request in providing work arrangements that may be better suited to their personal circumstances. In addition, variable leave options with procedures outlining applications for and use of personal leave, annual leave, long service leave, family violence leave, gender transition leave, IVF leave and parental leave are enshrined in the current Enterprise Award. Family Violence leave is recorded as a separate leave type. Northern Grampians Shire Council has taken active steps to attain more complete data on the reasons for female part time and casual participation in the workforce.
Gendered segregation within the workplace | Yes | The number of women in the category of professional increased from 67% to 75% , as did those in the technicians and trades workers category, from 5% to 11%. Council has recently implemented a new Learning and Development Platform which offers a wide range of Equality Courses/Programs. Council has also recently agreed on a new Enterprise Agreement (EA) which contains requirements for compulsory training against increment progression. The Learning and Development Platform and new EA have been used to deliver increased and consistent training on gender equality and as part of our ongoing commitment to ensure equality, we will be promoting these courses in our weekly learning and development calendar for the organisation to access.
Example(s)
Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  | a | b | c | d | e | f | g
Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled